## 20Feb23
Date | 2023-02-20
venue | Teams
Attendance
Sonia | y
Narinder | y
Godswill | y
Gideon PM | y
Ozomata | y
Item | Status | owner | Comment | Deadline | Status by next meeting
We introduced ourselves as this was the 1st meeting.
Gideon was the Project Manager for today’s meeting.
We introduced ourselves as this was the 1st meeting. Gideon was the Project Manager for today’s meeting. A Github Repository was created, and all members received an invitation to join. The expectation is for everyone to share processes along the way and monitor progress (we shouldn’t wait till the deadline before committing). https://github.com/gideonclottey/Bank-App.git
We reviewed the assessment/CRG to have a better understanding of the task at hand.
To ensure we follow agile processes short tasks have been assigned to all members using the We made use of the our Github Kanban (repository Project) to assign tasks.
To enable agile meetings, groups and workspaces were created on MS teams and slack respectively
To DO
Godswill was assigned to draft the user stories and share with Team members - | Open |  |  | 2023-02-20
Ozomata and Narinder to come up with the wireframe design, dependent on (1) above | open |  |  | TBD
Stand-up meeting to be held via Teams on 21/02/2023 by 12:00pm, Ozomata was assigned the Project Manager for the day with discussions to be centered around reviewing the user stories. |  |  |  | 2023-02-21

## 21Feb23
Date | 2023-02-21
venue | Teams
Attendance
Sonia
Narinder
Godswill
Gideon
Ozomata (PM)
Item | Status | owner | Comment | Deadline | Status by next meeting
Meeting Shedules (30-60 mins)
Minutes Suggestions Excel vs Other tools |  | PM for the day | keep the excel for now.
finalise User story and meeting minutes and commit | open | Godswill and Oz | PM must commit the minutes of the day Update Readme with User story
feedback on mockup -Narinder and Ozomata | open | Narinder &Oz | addintional task create logo | 2023-02-22
User acceptance criteria- Assignment and time line | open | Gideon &Sonia | MVP to be ready on or befor 5th March | 2023-02-23
Gannt chart creation -Assignment and timeline | open | oz |  | 2023-02-22
overview of all tools (python, django,UI UX tools Figma , PM tools (Teams,Slag,Git kanban, GanntProject) |  |  | 20X20X20 rule to be informed
Design stage |  |  | Dependent on Next meeting outcomes
AOB |  | Gideon | Stick to deadlines and be prepared
Next meeting |  | oz | after the CV class cafeteria | 23rd